# 05_Definitive_Agreements_Roadmap

HISN Platform

# DEFINITIVE AGREEMENTS ROADMAP

Date: 14 October 2026

## 1. Document Set

The following definitive agreements will be prepared after Term Sheet execution:

| # | Document | Purpose | Owner |
| --- | --- | --- | --- |
| 1 | Restated Articles of Association | Company constitution | Legal |
| 2 | Share Purchase Agreement (SPA) | Purchase of shares | Legal |
| 3 | Shareholders’ Agreement (SHA) | Governance + rights | Legal |
| 4 | Investor Rights Agreement (IRA) | Information + pro-rata | Legal |
| 5 | Founder Vesting Agreement | Vesting terms | Legal |
| 6 | IP Assignment Agreement | IP transfer | Legal |
| 7 | Employment Agreements | Founder + key hires | Legal |
| 8 | Non-Compete / Non-Solicit | Restrictions | Legal |
| 9 | Disclosure Schedule | Reps & warranties | Legal |
| 10 | Board Resolutions | Approvals | Company Secretary |
| 11 | Shareholder Resolutions | Approvals | Company Secretary |
| 12 | Officer’s Certificate | Compliance | CEO |
| 13 | Legal Opinion | Legal validity | Legal Counsel |
| 14 | Escrow Agreement (if any) | Fund holding | Legal |

## 2. Timeline

| Week | Milestone |
| --- | --- |
| 1 | Term sheet signed |
| 2-4 | Due diligence |
| 5-6 | Draft definitive agreements |
| 7-8 | Negotiation + revisions |
| 9 | Final versions |
| 10 | Board + shareholder approvals |
| 11 | Signing |
| 12 | Closing (payment + share issuance) |

## 3. Due Diligence Checklist

### Corporate

- Articles of Association

- Commercial Registration

- MISA license (if foreign)

- Board minutes

- Shareholder register

- Cap table (fully diluted)

### Legal

- Founder agreements

- Employment contracts

- IP assignments

- Vendor contracts

- Customer contracts

- Litigation search

### Financial

- Historical financials

- Bank statements

- Tax filings

- Debt schedule

- AR/AP aging

### Technical

- Architecture docs

- Source code ownership

- Open source scan

- Security assessment

### Compliance

- PDPL compliance

- Data classification

- Regulatory mapping

- Insurance policies

## 4. Closing Deliverables

| Deliverable | Owner | Date |
| --- | --- | --- |
| Executed SPA | Both | Closing |
| Executed SHA | All parties | Closing |
| Restated Articles | Company | Pre-closing |
| Board Resolutions | Company | Pre-closing |
| Shareholder Resolutions | Company | Pre-closing |
| Capital Injection | Investor | Closing |
| Share Certificate | Company | Closing |
| Updated Cap Table | Company | Closing |

## 5. Post-Closing

| Item | Timing |
| --- | --- |
| Update corporate records | Within 30 days |
| File with MISA (if needed) | Within 30 days |
| Notify ZATCA | Within 30 days |
| Update bank records | Within 30 days |
| Issue share certificates | Within 30 days |
| Board meeting (first) | Within 60 days |

## 6. Key Contacts

| Role | Name | Contact |
| --- | --- | --- |
| Company Legal Counsel | [TBD] | — |
| Investor Legal Counsel | [TBD] | — |
| Company Secretary | [TBD] | — |
| Notary | [TBD] | — |

This roadmap is indicative. Actual timeline depends on DD completion and negotiation.